## Sheet1
Product Backlog Refinement
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | User Authentication | Authentication | As a user, I want to securely log in and sign up using email and password. | Must | In Progress | 1. User can register and log in with valid credentials. 2. Passwords are securely stored and encrypted. 3. Users receive error messages for incorrect login attempts. | 1. Users must be able to register and log in. 2. The system must validate user credentials before granting access. 3. Users must be able to reset their password if forgotten. | 1. Authentication should complete within 2 seconds. 2. Passwords must be encrypted using AES-256 encryption. 3. OAuth 2.0 must be used for secure authentication. | 5 | TBD
2 | Budget Tracking | Core Features | As a user, I want to track my income and expenses easily. | Must | In Progress | 1. Users can add expenses with category and amount. 2. Users can view total spending for the month. 3. Users can filter expenses by category and date. | 1. Users must be able to add new expenses manually. 2. Users must be able to categorize expenses. 3. Users must be able to view total spending summaries. | 1. Expenses should be saved and retrieved within 2 seconds. 2. The system must support search and filtering for quick access. 3. The UI must provide clear visual representations of expenses. | 7 | TBD
3 | Goal Setting for Savings | Core Features | As a user, I want to set savings goals and track my progress. | Must | In Progress | 1. Users can create multiple savings goals. 2. Users can track progress based on transactions. 3. Users receive notifications when goals are close to completion. | 1. Users must be able to set savings goals. 2. The system must calculate progress automatically. 3. Users must receive alerts for goal milestones. | 1. Goal progress updates should be reflected in real-time. 2. The system must provide visual indicators (charts, graphs) for tracking. 3. Users must receive goal notifications within 5 seconds of reaching a milestone. | 6 | TBD
4 | Splitwise-style Expense Sharing | Expense Management | As a user, I want to split expenses with my friends and track who owes what. | Should | Backlog | 1. Users can create a shared expense group. 2. Users can add and split expenses within the group. 3. Users can settle balances with a single transaction. | 1. Users must be able to create and join shared expense groups. 2. Users must be able to add shared expenses. 3. The system must allow users to settle debts easily. | 1. Shared expense calculations should be updated within 3 seconds. 2. The system should support up to 50 users per group. 3. Balances must be accurately synchronized across all devices. | 8 | TBD
5 | Bank Integration (Plaid API) | Real-time Sync | As a user, I want my transactions to sync automatically with my bank. | Should | Backlog | 1. Users can securely connect their bank accounts. 2. Transactions sync automatically in real-time. 3. Users can categorize transactions fetched from the bank. | 1. Users must be able to securely link their bank accounts. 2. Transactions must be imported and categorized automatically. 3. Users must be able to review and edit imported transactions. | 1. Bank transactions should sync within 10 seconds. 2. All bank data must be encrypted and stored securely. 3. The system should categorize transactions with 90% accuracy. | 10 | TBD
6 | Investment Portfolio Tracking | Investment Features | As a user, I want to track my investment portfolio and see recommendations. | Could | Backlog | 1. Users can view real-time stock performance. 2. Users can add investments to their portfolio. 3. Users receive investment tips based on risk profile. | 1. Users must be able to track stocks in real time. 2. Users must be able to receive investment recommendations. 3. Users must be able to categorize and manage investments. | 1. Investment data should refresh every 30 seconds. 2. Stock charts should load within 3 seconds. 3. The system should use AI to tailor investment recommendations. | 12 | TBD
7 | Gamification & Leaderboard | Engagement | As a user, I want to compete with friends to save more and win rewards. | Could | Backlog | 1. Users can add friends to their savings leaderboard. 2. The leaderboard updates dynamically every month. 3. Users earn badges based on savings milestones. | 1. Users must be able to add friends to their leaderboard. 2. The leaderboard must rank users based on savings. 3. Users must receive rewards for achieving milestones. | 1. The leaderboard must update dynamically every 24 hours. 2. UI animations should be smooth and load within 1 second. 3. The system must handle up to 10,000 users without performance issues. | 8 | TBD
8 | Financial Education Content | Education | As a user, I want access to financial literacy resources. | Could | Backlog | 1. Users can browse financial articles and videos. 2. Content is updated regularly with new material. 3. Users receive recommendations based on preferences. | 1. Users must be able to browse and search financial content. 2. The system must update content periodically. 3. Users must receive personalized content recommendations. | 1. Content should load within 2 seconds. 2. The system must use AI to recommend personalized content. 3. Articles and videos must be optimized for mobile viewing. | 5 | TBD
9 | Notifications & Alerts | User Engagement | As a user, I want to receive alerts for bill payments and savings progress. | Should | Backlog | 1. Users receive reminders for upcoming bill payments. 2. Users are notified when they reach savings milestones. 3. Users can customize notification preferences. | 1. Users must receive timely notifications for bills and goals. 2. Users must be able to customize notification settings. 3. Notifications must be delivered via multiple channels (email, push). | 1. Notifications must be delivered within 2 seconds of the trigger. 2. Users should be able to configure notification preferences easily. 3. The system should support email, push, and SMS alerts. | 4 | TBD
10 | Multi-Currency Support | Global Features | As a user, I want to manage transactions in multiple currencies. | Could | Backlog | 1. Users can set their preferred default currency. 2. The system converts and displays amounts dynamically. 3. Exchange rates update in real-time. | 1. Users must be able to select a preferred currency. 2. The system must automatically convert values using real-time exchange rates. 3. The system must display transactions in the user's chosen currency. | 1. Exchange rates should update at least once per hour. 2. The currency conversion process should take no more than 2 seconds. 3. The system must cache exchange rates to reduce API calls. | 6 | TBD
11 | AI-Powered Expense Insights | Smart Expense Analytics | As a user, I want to receive AI-driven insights on my spending patterns so that I can optimize my budget and improve my savings. | Could | Backlog | 1.Users receive AI-driven insights based on spending habits. 2.System provides personalized budgeting recommendations. 3.Users can view categorized expense trends over time. | 1.The system must analyze users' spending patterns. 2.The system must generate and display insights dynamically. 3.Users must be able to access categorized spending reports. | 1.AI analysis should complete within 5 seconds. 2.Insights should be visually presented with easy-to-read graphs. 3.Recommendations should be updated dynamically based on new transactions. | 10 | TBD
12 | Subscription Management | Automated Subscription Tracking | As a user, I want to track and manage my recurring subscriptions so that I can avoid unnecessary charges and stay within budget. | Could | Backlog | 1.Users can add and manage subscriptions. 2.System automatically detects recurring transactions. 3.Users receive alerts for upcoming subscription payments. | 1.Users must be able to manually add subscription details. 2.The system must automatically detect recurring payments. 3.Users must be able to cancel or modify subscriptions. | 1.Subscription tracking should update in real-time. 2.Notifications for upcoming payments must be sent at least 24 hours in advance. 3.The system must handle up to 100 active subscriptions per user efficiently. | 7 | TBD
ID | Title | Role | Explanation
1 | User Authentication | Developer | Enables secure login and account management to protect user data and privacy.
2 | Budget Tracking | Product Owner | Helps users monitor their income, expenses, and spending habits to stay financially disciplined.
3 | Goal Setting for Savings | Product Owner | Allows users to define financial goals and track progress toward achieving them.
4 | Splitwise-style Expense Sharing | Developer | Facilitates shared expense tracking and settlements among friends, roommates, or groups.
5 | Bank Integration (Plaid API) | Scrum Master | Connects users’ bank accounts for automated transaction syncing and financial insights.
6 | Investment Portfolio Tracking | Scrum Master | Provides an overview of investments, stocks, and assets to monitor financial growth.
7 | Gamification & Leaderboard | Developer | Uses rewards, badges, and rankings to make financial management engaging and motivating.
8 | Financial Education Content | Product Owner | Offers articles, tips, and resources to improve users' financial knowledge and literacy.
9 | Notifications & Alerts | Scrum Master | Sends reminders and real-time alerts for bill payments, low balances, and spending trends.
10 | Multi-Currency Support | Developer | Allows users to track expenses and assets in different currencies for global financial management.
11 | Ai-Powered Expense Insights | Product Owner | AI analyzes spending and offers personalized budget tips.
12 | Subscription Management | Scrum Master | Tracks subscriptions and sends payment alerts.
| Deep Kakadiya | Developer | RA2211030010292
| Evan Mathew | Product Owner | RA2211030010277
| Megha Rao | Scrum Master | RA2211030010310